## RACI Matrix
Activity | Launch Manager | Site Leader | Operations Manager | HR Lead | Training Lead | IT Lead | Facilities Lead | Safety Lead | Security Lead | Transportation Lead | Finance Partner | Vendor Manager
Site Selection & Lease Approval | A | C | C |  |  |  | R |  |  |  | C
Facilities Build-Out | A | I |  |  |  |  | R | C |  |  |  | R
Network & Technology Install | A | I |  |  |  | R | [5 empty] | C
Hiring Plan & Recruiting | A | C | C | R
New Hire Training | I | A |  | C | R
Safety Audit & Certification | I | A |  |  |  |  | C | R
Operational Readiness Testing | A | R | R |  |  | C
Go/No-Go Decision | A | R | C |  |  |  |  | C | C
Day 1 Launch Execution | A | R | R | [6 empty] | R
Post-Launch Stabilization | A | R | R |  | C
Budget & Financial Tracking | A | I | [8 empty] | R
Vendor Delivery Management | C |  |  |  |  | C | C |  |  |  |  | R
R = Responsible A = Accountable C = Consulted I = Informed

## RAID Log
raid_id | site_id | type | description | category | severity | probability | owner | mitigation | due_date | status
R001 | DXP1 | Risk | WiFi coverage gaps in mezzanine area | Technology | Medium | Low | Ops Manager | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-07-17 | Escalated
R002 | DXP1 | Dependency | WMS go-live depends on network install completion | Technology | High | High | Safety Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-07-27 | Open
R003 | DXP1 | Issue | Safety audit found missing PPE inventory | Safety | Medium | Low | Safety Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-07-28 | Mitigating
R004 | DXP1 | Risk | Scanner devices delayed from vendor shipment | Technology | High | Medium | Vendor Manager | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-08-04 | Mitigating
R005 | DXP1 | Risk | Peak season volume may exceed site design capacity | Operational | High | Medium | Training Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-07-23 | Open
R006 | DXP2 | Assumption | Regional labor market will support hiring plan | People | Medium | Medium | Ops Manager | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-08-23 | Escalated
R007 | DXP2 | Dependency | WMS go-live depends on network install completion | Technology | High | High | HR Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-07-26 | Mitigating
R008 | DXP2 | Issue | Safety audit found missing PPE inventory | Safety | Medium | Low | IT Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-08-05 | Open
R009 | DXP3 | Issue | Background check turnaround exceeding SLA | People | Medium | Medium | Training Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-08-06 | Mitigating
R010 | DXP3 | Issue | Fire inspection failed on first attempt | Facilities | High | High | Site Leader | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-08-05 | Mitigating
R011 | DXP3 | Risk | Dock leveler installation behind schedule | Facilities | Medium | Medium | Ops Manager | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-09-01 | Mitigating
R012 | DXP4 | Risk | Transportation route conflicts with neighboring site | Operational | Low | Medium | IT Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-08-02 | Mitigating
R013 | DXP4 | Risk | Hiring pipeline below target for launch date | People | High | High | HR Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-07-29 | Open
R014 | DXP4 | Dependency | Route staging test depends on dock readiness | Operational | Medium | Medium | Facilities Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-07-18 | Closed
R015 | DXP5 | Risk | Transportation route conflicts with neighboring site | Operational | Low | Medium | Vendor Manager | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-09-06 | Open
R016 | DXP5 | Issue | Safety audit found missing PPE inventory | Safety | Medium | Low | Site Leader | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-09-02 | Open
R017 | DXP5 | Risk | Scanner devices delayed from vendor shipment | Technology | High | Medium | Facilities Lead | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-09-13 | Closed
R018 | DXP5 | Risk | Hiring pipeline below target for launch date | People | High | High | Vendor Manager | Escalate to vendor / accelerate parallel workstream / add contingency buffer | 2026-08-19 | Open

## Site Readiness Scorecard
site_id | site_name | region | launch_date | readiness_score | risk_score | schedule_variance_days | launch_confidence_score | go_no_go | open_blockers | critical_risks | delayed_milestones
DXP1 | Columbus East | Midwest | 2026-08-17 | 56.7 | 88.9 | 0 | 43.4 | NO-GO | 2 | 2 | 0
DXP2 | Charlotte South | Southeast | 2026-09-01 | 62.9 | 0 | -3 | 62.9 | CONDITIONAL GO | 1 | 0 | 1
DXP3 | Phoenix West | Southwest | 2026-09-14 | 61.1 | 66.7 | -5 | 51.1 | NO-GO | 0 | 0 | 0
DXP4 | Newark Metro | Northeast | 2026-08-24 | 58.8 | 66.7 | 4 | 46.4 | NO-GO | 1 | 1 | 0
DXP5 | Denver North | Mountain West | 2026-09-28 | 43 | 66.7 | 0 | 33 | NO-GO | 1 | 1 | 1

## Milestone Tracker
milestone_id | site_id | phase | planned_date | owner_dept | status | sequence
M001 | DXP1 | Site Planning | 2026-05-01 | Operations | Complete | 1
M002 | DXP1 | Facilities Readiness | 2026-05-13 | Facilities | Complete | 2
M003 | DXP1 | Technology Readiness | 2026-05-25 | Technology | Complete | 3
M004 | DXP1 | Hiring Readiness | 2026-06-06 | HR | Complete | 4
M005 | DXP1 | Training Readiness | 2026-06-18 | Training | On Track | 5
M006 | DXP1 | Safety Validation | 2026-06-30 | Safety | At Risk | 6
M007 | DXP1 | Operational Testing | 2026-07-12 | Operations | On Track | 7
M008 | DXP1 | Day 1 Launch | 2026-07-24 | Operations | On Track | 8
M009 | DXP1 | Post-Launch Stabilization | 2026-08-05 | Operations | Not Started | 9
M010 | DXP2 | Site Planning | 2026-05-16 | Operations | Complete | 1
M011 | DXP2 | Facilities Readiness | 2026-05-28 | Facilities | On Track | 2
M012 | DXP2 | Technology Readiness | 2026-06-09 | Technology | Blocked | 3
M013 | DXP2 | Hiring Readiness | 2026-06-21 | HR | Delayed | 4
M014 | DXP2 | Training Readiness | 2026-07-03 | Training | Complete | 5
M015 | DXP2 | Safety Validation | 2026-07-15 | Safety | On Track | 6
M016 | DXP2 | Operational Testing | 2026-07-27 | Operations | At Risk | 7
M017 | DXP2 | Day 1 Launch | 2026-08-08 | Operations | On Track | 8
M018 | DXP2 | Post-Launch Stabilization | 2026-08-20 | Operations | Not Started | 9
M019 | DXP3 | Site Planning | 2026-05-29 | Operations | At Risk | 1
M020 | DXP3 | Facilities Readiness | 2026-06-10 | Facilities | At Risk | 2
M021 | DXP3 | Technology Readiness | 2026-06-22 | Technology | Complete | 3
M022 | DXP3 | Hiring Readiness | 2026-07-04 | HR | Complete | 4
M023 | DXP3 | Training Readiness | 2026-07-16 | Training | On Track | 5
M024 | DXP3 | Safety Validation | 2026-07-28 | Safety | Complete | 6
M025 | DXP3 | Operational Testing | 2026-08-09 | Operations | Not Started | 7
M026 | DXP3 | Day 1 Launch | 2026-08-21 | Operations | At Risk | 8
M027 | DXP3 | Post-Launch Stabilization | 2026-09-02 | Operations | Not Started | 9
M028 | DXP4 | Site Planning | 2026-05-08 | Operations | Complete | 1
M029 | DXP4 | Facilities Readiness | 2026-05-20 | Facilities | Complete | 2
M030 | DXP4 | Technology Readiness | 2026-06-01 | Technology | At Risk | 3
M031 | DXP4 | Hiring Readiness | 2026-06-13 | HR | At Risk | 4
M032 | DXP4 | Training Readiness | 2026-06-25 | Training | Complete | 5
M033 | DXP4 | Safety Validation | 2026-07-07 | Safety | Complete | 6
M034 | DXP4 | Operational Testing | 2026-07-19 | Operations | Complete | 7
M035 | DXP4 | Day 1 Launch | 2026-07-31 | Operations | On Track | 8
M036 | DXP4 | Post-Launch Stabilization | 2026-08-12 | Operations | Not Started | 9
M037 | DXP5 | Site Planning | 2026-06-12 | Operations | Complete | 1
M038 | DXP5 | Facilities Readiness | 2026-06-24 | Facilities | Delayed | 2
M039 | DXP5 | Technology Readiness | 2026-07-06 | Technology | Complete | 3
M040 | DXP5 | Hiring Readiness | 2026-07-18 | HR | Complete | 4
M041 | DXP5 | Training Readiness | 2026-07-30 | Training | At Risk | 5
M042 | DXP5 | Safety Validation | 2026-08-11 | Safety | Not Started | 6
M043 | DXP5 | Operational Testing | 2026-08-23 | Operations | Not Started | 7
M044 | DXP5 | Day 1 Launch | 2026-09-04 | Operations | Not Started | 8
M045 | DXP5 | Post-Launch Stabilization | 2026-09-16 | Operations | Not Started | 9

## Task Detail
task_id | site_id | phase | task_name | owner_dept | due_date | status | priority
T0001 | DXP1 | Site Planning | Finalize site layout | Operations | 2026-04-26 | Delayed | High
T0002 | DXP1 | Site Planning | Confirm lease/permits | Operations | 2026-05-01 | At Risk | Low
T0003 | DXP1 | Site Planning | Approve headcount plan | Operations | 2026-04-29 | On Track | High
T0004 | DXP1 | Site Planning | Publish launch schedule | Operations | 2026-04-30 | Complete | High
T0005 | DXP1 | Facilities Readiness | Complete build-out | Facilities | 2026-05-08 | Complete | High
T0006 | DXP1 | Facilities Readiness | Install racking/conveyor | Facilities | 2026-05-08 | At Risk | Low
T0007 | DXP1 | Facilities Readiness | Fire inspection sign-off | Facilities | 2026-05-09 | On Track | High
T0008 | DXP1 | Facilities Readiness | Dock leveler install | Facilities | 2026-05-09 | At Risk | Medium
T0009 | DXP1 | Technology Readiness | Network/WiFi install | Technology | 2026-05-25 | Blocked | High
T0010 | DXP1 | Technology Readiness | Scanner provisioning | Technology | 2026-05-25 | At Risk | High
T0011 | DXP1 | Technology Readiness | WMS go-live config | Technology | 2026-05-24 | Complete | Low
T0012 | DXP1 | Technology Readiness | Badge access system live | Technology | 2026-05-21 | Complete | High
T0013 | DXP1 | Hiring Readiness | Post job requisitions | HR | 2026-06-02 | Complete | High
T0014 | DXP1 | Hiring Readiness | Complete hiring events | HR | 2026-06-01 | On Track | Low
T0015 | DXP1 | Hiring Readiness | Background checks cleared | HR | 2026-06-01 | Complete | Low
T0016 | DXP1 | Hiring Readiness | Offer acceptance target met | HR | 2026-06-03 | Complete | High
T0017 | DXP1 | Training Readiness | Trainer certification | Training | 2026-06-15 | Complete | Low
T0018 | DXP1 | Training Readiness | New hire orientation scheduled | Training | 2026-06-16 | Complete | High
T0019 | DXP1 | Training Readiness | SOP training completed | Training | 2026-06-17 | Complete | Low
T0020 | DXP1 | Training Readiness | Safety training completed | Training | 2026-06-15 | On Track | Medium
T0021 | DXP1 | Safety Validation | Safety audit passed | Safety | 2026-06-28 | Complete | High
T0022 | DXP1 | Safety Validation | PPE stock confirmed | Safety | 2026-06-29 | On Track | Medium
T0023 | DXP1 | Safety Validation | Emergency evacuation plan posted | Safety | 2026-06-30 | On Track | High
T0024 | DXP1 | Safety Validation | Incident escalation tested | Safety | 2026-06-27 | Complete | High
T0025 | DXP1 | Operational Testing | Scanner load test | Operations | 2026-07-10 | Complete | Medium
T0026 | DXP1 | Operational Testing | Route staging dry run | Operations | 2026-07-08 | Complete | Medium
T0027 | DXP1 | Operational Testing | Dock throughput test | Operations | 2026-07-12 | Delayed | Low
T0028 | DXP1 | Operational Testing | Peak volume simulation | Operations | 2026-07-09 | Blocked | Low
T0029 | DXP1 | Day 1 Launch | Leadership sign-off obtained | Operations | 2026-07-24 | Complete | Medium
T0030 | DXP1 | Day 1 Launch | Day 1 staffing confirmed | Operations | 2026-07-24 | Complete | Low
T0031 | DXP1 | Day 1 Launch | Go/No-Go review completed | Operations | 2026-07-22 | On Track | Low
T0032 | DXP1 | Day 1 Launch | Launch war room staffed | Operations | 2026-07-20 | Complete | Medium
T0033 | DXP1 | Post-Launch Stabilization | Daily stand-ups (Week 1) | Operations | 2026-08-01 | Not Started | High
T0034 | DXP1 | Post-Launch Stabilization | Defect/issue log review | Operations | 2026-07-31 | Not Started | High
T0035 | DXP1 | Post-Launch Stabilization | 30-day performance review | Operations | 2026-08-05 | Not Started | Low
T0036 | DXP1 | Post-Launch Stabilization | Lessons learned session | Operations | 2026-08-04 | Not Started | Medium
T0037 | DXP2 | Site Planning | Finalize site layout | Operations | 2026-05-16 | On Track | High
T0038 | DXP2 | Site Planning | Confirm lease/permits | Operations | 2026-05-16 | Complete | Medium
T0039 | DXP2 | Site Planning | Approve headcount plan | Operations | 2026-05-14 | Delayed | Medium
T0040 | DXP2 | Site Planning | Publish launch schedule | Operations | 2026-05-11 | Complete | Medium
T0041 | DXP2 | Facilities Readiness | Complete build-out | Facilities | 2026-05-27 | Complete | Medium
T0042 | DXP2 | Facilities Readiness | Install racking/conveyor | Facilities | 2026-05-26 | On Track | High
T0043 | DXP2 | Facilities Readiness | Fire inspection sign-off | Facilities | 2026-05-23 | On Track | Medium
T0044 | DXP2 | Facilities Readiness | Dock leveler install | Facilities | 2026-05-23 | Complete | Low
T0045 | DXP2 | Technology Readiness | Network/WiFi install | Technology | 2026-06-04 | At Risk | High
T0046 | DXP2 | Technology Readiness | Scanner provisioning | Technology | 2026-06-05 | Delayed | Low
T0047 | DXP2 | Technology Readiness | WMS go-live config | Technology | 2026-06-08 | Delayed | Low
T0048 | DXP2 | Technology Readiness | Badge access system live | Technology | 2026-06-04 | On Track | High
T0049 | DXP2 | Hiring Readiness | Post job requisitions | HR | 2026-06-20 | Complete | Medium
T0050 | DXP2 | Hiring Readiness | Complete hiring events | HR | 2026-06-18 | Complete | Medium
T0051 | DXP2 | Hiring Readiness | Background checks cleared | HR | 2026-06-16 | Complete | Low
T0052 | DXP2 | Hiring Readiness | Offer acceptance target met | HR | 2026-06-17 | Complete | High
T0053 | DXP2 | Training Readiness | Trainer certification | Training | 2026-06-28 | Complete | Medium
T0054 | DXP2 | Training Readiness | New hire orientation scheduled | Training | 2026-07-03 | At Risk | High
T0055 | DXP2 | Training Readiness | SOP training completed | Training | 2026-07-03 | Complete | Medium
T0056 | DXP2 | Training Readiness | Safety training completed | Training | 2026-06-30 | Complete | Medium
T0057 | DXP2 | Safety Validation | Safety audit passed | Safety | 2026-07-15 | Complete | High
T0058 | DXP2 | Safety Validation | PPE stock confirmed | Safety | 2026-07-11 | At Risk | Low
T0059 | DXP2 | Safety Validation | Emergency evacuation plan posted | Safety | 2026-07-13 | Complete | High
T0060 | DXP2 | Safety Validation | Incident escalation tested | Safety | 2026-07-10 | Blocked | Medium
T0061 | DXP2 | Operational Testing | Scanner load test | Operations | 2026-07-24 | Complete | Low
T0062 | DXP2 | Operational Testing | Route staging dry run | Operations | 2026-07-24 | Complete | High
T0063 | DXP2 | Operational Testing | Dock throughput test | Operations | 2026-07-25 | At Risk | High
T0064 | DXP2 | Operational Testing | Peak volume simulation | Operations | 2026-07-26 | At Risk | Low
T0065 | DXP2 | Day 1 Launch | Leadership sign-off obtained | Operations | 2026-08-04 | Not Started | Low
T0066 | DXP2 | Day 1 Launch | Day 1 staffing confirmed | Operations | 2026-08-06 | Not Started | Low
T0067 | DXP2 | Day 1 Launch | Go/No-Go review completed | Operations | 2026-08-04 | Not Started | Medium
T0068 | DXP2 | Day 1 Launch | Launch war room staffed | Operations | 2026-08-04 | Not Started | Medium
T0069 | DXP2 | Post-Launch Stabilization | Daily stand-ups (Week 1) | Operations | 2026-08-18 | Not Started | High
T0070 | DXP2 | Post-Launch Stabilization | Defect/issue log review | Operations | 2026-08-19 | Not Started | Low
T0071 | DXP2 | Post-Launch Stabilization | 30-day performance review | Operations | 2026-08-17 | Not Started | High
T0072 | DXP2 | Post-Launch Stabilization | Lessons learned session | Operations | 2026-08-20 | Not Started | High
T0073 | DXP3 | Site Planning | Finalize site layout | Operations | 2026-05-28 | At Risk | Low
T0074 | DXP3 | Site Planning | Confirm lease/permits | Operations | 2026-05-28 | Complete | Low
T0075 | DXP3 | Site Planning | Approve headcount plan | Operations | 2026-05-26 | Complete | Low
T0076 | DXP3 | Site Planning | Publish launch schedule | Operations | 2026-05-29 | Complete | Medium
T0077 | DXP3 | Facilities Readiness | Complete build-out | Facilities | 2026-06-07 | On Track | Low
T0078 | DXP3 | Facilities Readiness | Install racking/conveyor | Facilities | 2026-06-07 | Complete | Low
T0079 | DXP3 | Facilities Readiness | Fire inspection sign-off | Facilities | 2026-06-08 | Complete | Low
T0080 | DXP3 | Facilities Readiness | Dock leveler install | Facilities | 2026-06-10 | Complete | Low
T0081 | DXP3 | Technology Readiness | Network/WiFi install | Technology | 2026-06-17 | At Risk | High
T0082 | DXP3 | Technology Readiness | Scanner provisioning | Technology | 2026-06-17 | On Track | Low
T0083 | DXP3 | Technology Readiness | WMS go-live config | Technology | 2026-06-20 | Delayed | Low
T0084 | DXP3 | Technology Readiness | Badge access system live | Technology | 2026-06-20 | On Track | High
T0085 | DXP3 | Hiring Readiness | Post job requisitions | HR | 2026-07-02 | At Risk | Medium
T0086 | DXP3 | Hiring Readiness | Complete hiring events | HR | 2026-07-03 | At Risk | Medium
T0087 | DXP3 | Hiring Readiness | Background checks cleared | HR | 2026-07-04 | On Track | Low
T0088 | DXP3 | Hiring Readiness | Offer acceptance target met | HR | 2026-06-29 | At Risk | Medium
T0089 | DXP3 | Training Readiness | Trainer certification | Training | 2026-07-12 | On Track | High
T0090 | DXP3 | Training Readiness | New hire orientation scheduled | Training | 2026-07-12 | Complete | High
T0091 | DXP3 | Training Readiness | SOP training completed | Training | 2026-07-11 | Complete | Medium
T0092 | DXP3 | Training Readiness | Safety training completed | Training | 2026-07-11 | Complete | Low
T0093 | DXP3 | Safety Validation | Safety audit passed | Safety | 2026-07-24 | On Track | High
T0094 | DXP3 | Safety Validation | PPE stock confirmed | Safety | 2026-07-27 | Complete | Medium
T0095 | DXP3 | Safety Validation | Emergency evacuation plan posted | Safety | 2026-07-27 | On Track | Low
T0096 | DXP3 | Safety Validation | Incident escalation tested | Safety | 2026-07-24 | Delayed | High
T0097 | DXP3 | Operational Testing | Scanner load test | Operations | 2026-08-05 | Not Started | Medium
T0098 | DXP3 | Operational Testing | Route staging dry run | Operations | 2026-08-06 | Not Started | High
T0099 | DXP3 | Operational Testing | Dock throughput test | Operations | 2026-08-09 | Not Started | Medium
T0100 | DXP3 | Operational Testing | Peak volume simulation | Operations | 2026-08-07 | Not Started | High
T0101 | DXP3 | Day 1 Launch | Leadership sign-off obtained | Operations | 2026-08-21 | Not Started | High
T0102 | DXP3 | Day 1 Launch | Day 1 staffing confirmed | Operations | 2026-08-17 | Not Started | High
T0103 | DXP3 | Day 1 Launch | Go/No-Go review completed | Operations | 2026-08-21 | Not Started | Low
T0104 | DXP3 | Day 1 Launch | Launch war room staffed | Operations | 2026-08-18 | Not Started | High
T0105 | DXP3 | Post-Launch Stabilization | Daily stand-ups (Week 1) | Operations | 2026-08-29 | Not Started | High
T0106 | DXP3 | Post-Launch Stabilization | Defect/issue log review | Operations | 2026-09-01 | Not Started | Low
T0107 | DXP3 | Post-Launch Stabilization | 30-day performance review | Operations | 2026-08-30 | Not Started | Low
T0108 | DXP3 | Post-Launch Stabilization | Lessons learned session | Operations | 2026-09-01 | Not Started | Medium
T0109 | DXP4 | Site Planning | Finalize site layout | Operations | 2026-05-04 | Complete | Low
T0110 | DXP4 | Site Planning | Confirm lease/permits | Operations | 2026-05-05 | At Risk | High
T0111 | DXP4 | Site Planning | Approve headcount plan | Operations | 2026-05-04 | Complete | Low
T0112 | DXP4 | Site Planning | Publish launch schedule | Operations | 2026-05-03 | Complete | High
T0113 | DXP4 | Facilities Readiness | Complete build-out | Facilities | 2026-05-15 | Complete | Medium
T0114 | DXP4 | Facilities Readiness | Install racking/conveyor | Facilities | 2026-05-17 | Delayed | Low
T0115 | DXP4 | Facilities Readiness | Fire inspection sign-off | Facilities | 2026-05-15 | At Risk | Medium
T0116 | DXP4 | Facilities Readiness | Dock leveler install | Facilities | 2026-05-17 | On Track | Low
T0117 | DXP4 | Technology Readiness | Network/WiFi install | Technology | 2026-05-29 | At Risk | High
T0118 | DXP4 | Technology Readiness | Scanner provisioning | Technology | 2026-05-31 | Complete | High
T0119 | DXP4 | Technology Readiness | WMS go-live config | Technology | 2026-06-01 | Delayed | Medium
T0120 | DXP4 | Technology Readiness | Badge access system live | Technology | 2026-06-01 | On Track | Low
T0121 | DXP4 | Hiring Readiness | Post job requisitions | HR | 2026-06-09 | Delayed | High
T0122 | DXP4 | Hiring Readiness | Complete hiring events | HR | 2026-06-09 | Complete | High
T0123 | DXP4 | Hiring Readiness | Background checks cleared | HR | 2026-06-13 | Complete | High
T0124 | DXP4 | Hiring Readiness | Offer acceptance target met | HR | 2026-06-08 | Complete | Low
T0125 | DXP4 | Training Readiness | Trainer certification | Training | 2026-06-25 | At Risk | High
T0126 | DXP4 | Training Readiness | New hire orientation scheduled | Training | 2026-06-25 | At Risk | High
T0127 | DXP4 | Training Readiness | SOP training completed | Training | 2026-06-23 | Complete | High
T0128 | DXP4 | Training Readiness | Safety training completed | Training | 2026-06-21 | On Track | High
T0129 | DXP4 | Safety Validation | Safety audit passed | Safety | 2026-07-05 | Complete | Low
T0130 | DXP4 | Safety Validation | PPE stock confirmed | Safety | 2026-07-04 | Complete | High
T0131 | DXP4 | Safety Validation | Emergency evacuation plan posted | Safety | 2026-07-03 | Complete | High
T0132 | DXP4 | Safety Validation | Incident escalation tested | Safety | 2026-07-02 | Delayed | Low
T0133 | DXP4 | Operational Testing | Scanner load test | Operations | 2026-07-15 | On Track | Medium
T0134 | DXP4 | Operational Testing | Route staging dry run | Operations | 2026-07-18 | At Risk | Medium
T0135 | DXP4 | Operational Testing | Dock throughput test | Operations | 2026-07-16 | Complete | High
T0136 | DXP4 | Operational Testing | Peak volume simulation | Operations | 2026-07-19 | Blocked | High
T0137 | DXP4 | Day 1 Launch | Leadership sign-off obtained | Operations | 2026-07-26 | Complete | Medium
T0138 | DXP4 | Day 1 Launch | Day 1 staffing confirmed | Operations | 2026-07-29 | On Track | Medium
T0139 | DXP4 | Day 1 Launch | Go/No-Go review completed | Operations | 2026-07-28 | Complete | Medium
T0140 | DXP4 | Day 1 Launch | Launch war room staffed | Operations | 2026-07-26 | Complete | High
T0141 | DXP4 | Post-Launch Stabilization | Daily stand-ups (Week 1) | Operations | 2026-08-07 | Not Started | Low
T0142 | DXP4 | Post-Launch Stabilization | Defect/issue log review | Operations | 2026-08-07 | Not Started | High
T0143 | DXP4 | Post-Launch Stabilization | 30-day performance review | Operations | 2026-08-12 | Not Started | Medium
T0144 | DXP4 | Post-Launch Stabilization | Lessons learned session | Operations | 2026-08-07 | Not Started | Medium
T0145 | DXP5 | Site Planning | Finalize site layout | Operations | 2026-06-12 | On Track | High
T0146 | DXP5 | Site Planning | Confirm lease/permits | Operations | 2026-06-11 | On Track | High
T0147 | DXP5 | Site Planning | Approve headcount plan | Operations | 2026-06-08 | Complete | Medium
T0148 | DXP5 | Site Planning | Publish launch schedule | Operations | 2026-06-11 | Complete | Medium
T0149 | DXP5 | Facilities Readiness | Complete build-out | Facilities | 2026-06-23 | Complete | Medium
T0150 | DXP5 | Facilities Readiness | Install racking/conveyor | Facilities | 2026-06-21 | Complete | High
T0151 | DXP5 | Facilities Readiness | Fire inspection sign-off | Facilities | 2026-06-24 | On Track | Medium
T0152 | DXP5 | Facilities Readiness | Dock leveler install | Facilities | 2026-06-20 | Blocked | High
T0153 | DXP5 | Technology Readiness | Network/WiFi install | Technology | 2026-07-06 | On Track | Low
T0154 | DXP5 | Technology Readiness | Scanner provisioning | Technology | 2026-07-02 | At Risk | High
T0155 | DXP5 | Technology Readiness | WMS go-live config | Technology | 2026-07-06 | Complete | High
T0156 | DXP5 | Technology Readiness | Badge access system live | Technology | 2026-07-05 | At Risk | Medium
T0157 | DXP5 | Hiring Readiness | Post job requisitions | HR | 2026-07-15 | On Track | Medium
T0158 | DXP5 | Hiring Readiness | Complete hiring events | HR | 2026-07-17 | On Track | Medium
T0159 | DXP5 | Hiring Readiness | Background checks cleared | HR | 2026-07-18 | On Track | High
T0160 | DXP5 | Hiring Readiness | Offer acceptance target met | HR | 2026-07-15 | Complete | High
T0161 | DXP5 | Training Readiness | Trainer certification | Training | 2026-07-27 | Complete | Medium
T0162 | DXP5 | Training Readiness | New hire orientation scheduled | Training | 2026-07-27 | Complete | Medium
T0163 | DXP5 | Training Readiness | SOP training completed | Training | 2026-07-27 | Complete | Low
T0164 | DXP5 | Training Readiness | Safety training completed | Training | 2026-07-25 | On Track | Low
T0165 | DXP5 | Safety Validation | Safety audit passed | Safety | 2026-08-06 | Not Started | Low
T0166 | DXP5 | Safety Validation | PPE stock confirmed | Safety | 2026-08-08 | Not Started | High
T0167 | DXP5 | Safety Validation | Emergency evacuation plan posted | Safety | 2026-08-10 | Not Started | Medium
T0168 | DXP5 | Safety Validation | Incident escalation tested | Safety | 2026-08-10 | Not Started | High
T0169 | DXP5 | Operational Testing | Scanner load test | Operations | 2026-08-19 | Not Started | Low
T0170 | DXP5 | Operational Testing | Route staging dry run | Operations | 2026-08-19 | Not Started | High
T0171 | DXP5 | Operational Testing | Dock throughput test | Operations | 2026-08-18 | Not Started | Medium
T0172 | DXP5 | Operational Testing | Peak volume simulation | Operations | 2026-08-23 | Not Started | High
T0173 | DXP5 | Day 1 Launch | Leadership sign-off obtained | Operations | 2026-08-31 | Not Started | Medium
T0174 | DXP5 | Day 1 Launch | Day 1 staffing confirmed | Operations | 2026-08-31 | Not Started | Low
T0175 | DXP5 | Day 1 Launch | Go/No-Go review completed | Operations | 2026-09-03 | Not Started | High
T0176 | DXP5 | Day 1 Launch | Launch war room staffed | Operations | 2026-08-31 | Not Started | High
T0177 | DXP5 | Post-Launch Stabilization | Daily stand-ups (Week 1) | Operations | 2026-09-15 | Not Started | High
T0178 | DXP5 | Post-Launch Stabilization | Defect/issue log review | Operations | 2026-09-12 | Not Started | High
T0179 | DXP5 | Post-Launch Stabilization | 30-day performance review | Operations | 2026-09-11 | Not Started | High
T0180 | DXP5 | Post-Launch Stabilization | Lessons learned session | Operations | 2026-09-13 | Not Started | High